## STAKEHOLDER Mngm
Last Update | 2024-11-28 |  |  | Overall Stakeholder Temperatur | 9
Next Update | 2024-12-19 |  |  | Overall Stakeholder Impact | 7
STAKEHOLDERS | [7 empty] | ASSESMENT |  |  | COMMITMENT |  | DESCRIPTION |  |  |  | MANAGEMENT STRATEGY
Pic | Name | Role/Position | Partners | Internal Relations | Contact | Type | Status | Interest Level | Influence Level | Project Impact | Current Commitment | Temperature | Expectations | Personal Goals | Potential Impact on Project | What activities directly involve or impact the stakeholder? | Management Strategy | Communication Plan | Meeting Name | Meeting Frequency | Meeting Schedule | Expected Deliverables | Document Owner
#VALUE! | Marta Len | VP of Delivery | 1 | Oversees Program Manager; coordinates with COO for resource approvals; collaborates with DBT on prioritization and strategic alignment. | Email: marlen@company.com Mobile: (+55) 000 000 111 Working Hours: 8:00-16:00 (CET) Contact: Whatsapp /Teams /Email | Internal | Active | 3 | 3 | 9 | 1 | 9 | On-time, on-budget delivery aligned with strategic objectives | 1. Highly motivated to ensure successful delivery for career visibility; 2. Values team recognition and project-wide collaboration. | Direct influence over resources, priorities, and escalations | Resource allocation, strategic alignment, escalations | Maintain close alignment on strategic objectives; involve in resource planning discussions; ensure escalations are resolved promptly. | Quartely executive reports; ad-hoc escalation meetings | EXECUTIVES SYNC CALL | QUARTERLY | First Tuesday 14:30 CET | Executive Summary: Key updates, risks, mitigations; Budget Performance Report | Program Manager (Delivery-side)
#VALUE! | Thomas Williams | Chief Operating Officer | 1 | Holds formal authority over resource allocation; works closely with the Business Sponsor to ensure operational alignment; informally influences strategic priorities. | Email: twilliams@client.com Mobile: (+55) 666 777 444 Working Hours: 11:00-19:00 (CET) Contact: Whatsapp / Teams / Email | External | Active | 1 | 3 | 3 | 2 | 6 | Project enhances operational efficiency and profitability | 1. Seeks to enhance reputation by delivering high-value projects; 2. Recently considering retirement and prefers minimal disruptions. | Can approve or halt the project; allocate or withdraw resources | Approval of budget; resource allocation; review of project impact on operations | Focus on high-level strategic value and minimal disruption; avoid overloading with details; frame updates in terms of operational efficiency. | Quarterly executive summaries; participate in key milestone reviews | EXECUTIVES SYNC CALL | QUARTERLY | First Tuesday 14:30 CET | One-pager report: Project status, traffic lights (risk, budget, timeline), achievements, blockers; Resource Allocation Summary | VP of Delivery (Delivery-side)
#VALUE! | Autumn Silva | Program Manager | 2 | Reports to VP of Delivery; collaborates formally with Project Manager and DBT; influences solution direction via Solution Architect. | Email: autsilv@company.com Mobile: (+49) 000 333 444 Working Hours: 8:00-16:00 (CET) Contact: Whatsapp / Teams / Email | Internal | Active | 3 | 3 | 9 | 2 | 18 | Efficient inter-project coordination; program-level alignment | 1. Motivated by delivering a well-coordinated program to enhance reputation; 2. Recently taken on additional responsibilities across other projects. | Direct influence over program resources and interdependencies | Coordination of interdependencies; managing cross-project risks | Provide clear prioritization and scheduling; streamline communications to avoid overload; acknowledge program-level contributions. | Monthly interanal steering committee meetings; and steering sync with client | STEERING SYNC CALL | MONTHLY | First Wednesday 14:30 CET | Program Status Report: Dependencies, risks, milestones; Interdependency Tracking Document | Program Manager (Delivery-side)
#VALUE! | Martin Stachursky | Director of Business Transformation | 2 | Formally reports to COO; collaborates with Business Sponsor on transformation initiatives; influences IT Enterprise Architect and Project Manager. | Email: mstachursky@client.com Mobile: (+55) 111 333 888 Working Hours: 11:00-19:00 (CET) Contact: Whatsapp / Teams / Email | External | Active | 3 | 3 | 9 | 1 | 9 | Alignment with transformation initiatives; ROI realization | 1. Seeks a promotion tied to successful project outcomes; 2. Highly focused on timely delivery and measurable ROI. | Influence over strategic direction; resource prioritization | Program alignment; review of transformation milestones; prioritization of deliverables | Engage closely in strategic decisions; provide regular updates demonstrating ROI progress; highlight alignment with company goals. | Monthly strategy meetings; detailed progress reports | STEERING SYNC CALL | MONTHLY | First Wednesday 14:30 CET | Transformation Update Report: Status on strategic alignment, major risks, milestones, ROI; Risk Register with mitigation actions | Program Manager (Delivery-side)
#VALUE! | Gabriela Sousa | Business Sponsor | 3 | Collaborates formally with COO on strategic alignment; has informal influence over IT Operations Manager and IT Enterprise Architect. | Email: gsousa@client.com Mobile: (+55) 000 333 444 Working Hours: 11:00-19:00 (CET) Contact: Whatsapp / Teams / Email | External | Active | 3 | 3 | 9 | 1 | 9 | Improved sales processes; increased sales revenue | 1. Ambitious and sees project success as an opportunity for internal recognition and team development; 2.Frustrated with resource constraints. | Can champion or obstruct the project; influence user adoption | Requirements validation; process design approval; UAT coordination | Ensure consistent engagement in decision-making; provide visibility into resource allocation and celebrate incremental project milestones. | Weekly status meetings; decision-making sessions | PROJECT SYNC CALL | WEEKLY | Thursday 14:30 CET | Weekly Progress Dashboard: Achievements, blockers, risks, actions; UAT Summary Report | Project Manager (Delivery-side)
#VALUE! | Tobias Mueller | Project Manager | 3 | Collaborates closely with Program Manager and Solution Architect; manages interactions with Business Sponsor and COO for issue resolution. | Email: tobmuel@company.com Mobile: (+49) 123 456 789 Working Hours: 8:00-16:00 (CET) Contact: Whatsapp / Teams / Email | Internal | Active | 3 | 3 | 9 | 1 | 9 | Successful project delivery; stakeholder satisfaction | 1. Focused on building delivery credibility; 2. Perceives risks tied to delays as threats to career trajectory. | Directly manages project execution and deliverables | Day-to-day execution; risk and issue tracking; stakeholder engagement | Empower with decision-making authority; provide clear pathways to escalate issues; ensure public recognition for delivery milestones. | Daily team updates; weekly status reports | PROJECT SYNC CALL | WEEKLY | Thursday 14:30 CET | Weekly Progress Dashboard: Achievements, blockers, risks, actions; UAT Summary Report | Project Manager (Delivery-side)
#VALUE! | Mark Erikson | IT Enterprise Architect (ITEA) | 4 | Collaborates formally with IT Operations Manager and Technical Lead; ensures technical designs align with overall architecture. | Email: merikson@client.com Working Hours: 11:00-19:00 (CET) Contact: Teams /Email | External | Active | 3 | 2 | 6 | 1 | 6 | Technical alignment; seamless integration | 1. Recently promoted and under pressure to prove competence; 2. Perceives the project as a platform to demonstrate expertise. | Approval of technical designs; impact on integration success | Technical design reviews; integration planning; infrastructure alignment | Involve in key technical decisions; acknowledge contributions publicly; provide structured opportunities to showcase expertise. | Regular technical design meetings; documentation sharing | PROJECT SYNC CALL | WEEKLY | Thursday 14:30 CET | Technical Design Document: Architecture diagrams, technical specifications; Integration Plan | Solution Architect (Delivery-side)
#VALUE! | Ana Faris | Solution Architect | 4 | Reports to Project Manager; collaborates with IT Enterprise Architect and Technical Lead; ensures alignment with DBT and Program Manager. | Email: anafar@company.com Working Hours: 8:00-16:00 (CET) Contact: Teams/e-Mail | Internal | Active | 3 | 2 | 6 | 1 | 6 | Technical solution meets business and technical needs | 1. Recently transitioned to the role; 2. Highly motivated to deliver innovative, impactful solutions for future career opportunities. | Direct influence on design feasibility and implementation success | Designing the architecture; reviewing integration and infrastructure needs | Provide structured feedback channels for innovation; involve in visible design presentations; acknowledge technical contributions publicly. | Weekly design reviews; architecture documentation updates | PROJECT SYNC CALL | WEEKLY | Thursday 14:30 CET | Solution Architecture Review: Designs, reviews; Change Requests Log | Solution Architect (Delivery-side)
#VALUE! | Adam Smith | Tech Lead | 5 | Reports to Project Manager; collaborates with IT Operations Manager and Solution Architect for execution; leads the development team. | Email: adasmi@company.com Working Hours: 8:00-16:00 (CET) Contact: Teams/e-Mail | Internal | Active | 3 | 2 | 6 | 1 | 6 | Quality technical execution; issue resolution | 1. Managing workload stress due to increased team responsibilities; 2. Balancing technical and leadership challenges. | Manages technical teams; resolves blockers in implementation | Development and configuration; resolving technical blockers | Offer resources to alleviate pressure; provide targeted recognition for efforts; involve in strategic technical discussions for empowerment. | Daily stand-ups; weekly technical updates | PROJECT SYNC CALL | WEEKLY | Thursday 14:30 CET | Technical Progress Report: Development status, blockers; Code Review Notes | Technical Lead (Delivery-side)
#VALUE! | Olivia Davis | IT Operations Manager (ITOM) | 5 | Reports to COO; collaborates with IT Enterprise Architect and Technical Lead on technical readiness. | Email: odavis@client.com Working Hours: 11:00-19:00 (CET) Contact: Teams /Email | External | Active | 2 | 2 | 4 | 3 | 12 | Minimal disruption; operational readiness | 1. Concerned about resource overload due to staff shortages; 2.Views the project as a risk to operational stability. | Influence on system integration; support during implementation | Testing support; review of operational impact; readiness for system go-live | Mitigate workload concerns; emphasize long-term operational benefits; involve early in planning to address resource and risk issues. | Weekly technical updates; involve in testing and deployment | PROJECT SYNC CALL | WEEKLY | Thursday 14:30 CET | Operational Readiness Checklist: Deployment dependencies, risks; Go-Live Approval Document | Technical Lead (Delivery-side)
[8 empty] | 3 | 3 | 6 | 9
[8 empty] | 2 | 2 | 4 | 6
[8 empty] | 1 | 1 | 2 | 3
[9 empty] | 1 | 2 | 3
[8 empty] | 3 | 3 | 6 | 9 | 12 | 18 | 27
[8 empty] | 2 | 2 | 4 | 6 | 8 | 12 | 18
[8 empty] | 1 | 1 | 2 | 3 | 4 | 6 | 9
[9 empty] | 1 | 2 | 3 | 4 | 6 | 9